# AgroSense AI: Execution Plan

Hybrid IoT and Web-Based Intelligent Crop Monitoring and Prediction System

Assumptions: crop irrigation track (the PDF builds everything around it, and it has better public datasets than air quality), about 8 weeks, 3 members. If your deadline is shorter, merge Weeks 5-6 and cut the explainability work first.

## Week 1: Freeze the scope

- Decide the track. The PDF's only open question is irrigation vs. air quality. Pick irrigation and don't revisit it.

- Pick one crop and one soil context. Everything is trained and demoed around that.

- Fix the model inputs to what the hardware can supply: soil moisture, temperature, humidity.

- Fix the outputs: water-stress risk (Low/Medium/High) and irrigation recommendation (Needed/Monitor/Not needed).

- Defer forecasting. The PDF itself says it needs time-series data you won't have, so list it as future work.

- Write the API contract (JSON request/response) so all three of you can work in parallel without waiting on each other.

- Set up one Git repo with /backend, /ml-service, /frontend, /firmware, /docs.

## Weeks 1-2: Data (Member 2 leads)

- Shortlist 2-3 public agricultural or irrigation datasets (Kaggle, UCI).

- Check for each one whether it has your three features and a usable target label. This is the PDF's "first job".

- If no dataset has a real target, derive labels from documented agronomic thresholds for your crop. State this openly in the report, because the model will then be learning your rules, and a reviewer will ask.

- Clean the data, handle missing values, and normalize units to match what your sensors output.

- Decide whether the train/test split is random or grouped. A grouped split is more honest if the data has repeated records.

## Weeks 2-4: Parallel build

| Member | Work |
| --- | --- |
| Md. Tahmidul Alam Ahad | ASP.NET Core API, NeonDB schema (devices, sensor_readings, predictions), validation layer, ESP32 ingestion endpoint, Follow Clean Architecture |
| Abdur Rahman | Baseline models (Logistic Regression, Random Forest, XGBoost), tuning, evaluation, feature importance/SHAP, export model, wrap in FastAPI /predict |
| Mohammad Tareq Aziz | React app: manual input form, live readings view, prediction card, history chart, alerts |

Endpoints to build:

- POST /api/readings: ESP32 sends data

- POST /api/predict/manual: web form input

- GET /api/readings/latest and GET /api/predictions/history: dashboard data

Both input modes must go through the same validation, same preprocessing, same model. That is what the PDF's research question rests on.

Hardware (unassigned in the PDF, so assign it now): the ESP32 firmware reads the soil moisture sensor and DHT22, then sends HTTP POSTs every few seconds. Calibrate the soil sensor in air (dry) and in water (wet), then map the raw readings to a percentage. Bad calibration will make the model look wrong at demo time.

## Week 5: Integration

- Connect ASP.NET Core to the FastAPI service and store each prediction in the DB.

- Connect React to the API.

- Run an end-to-end test: ESP32 → API → model → DB → dashboard, and manual form → same path.

- Handle failure cases: device offline, ML service down, out-of-range values.

## Week 6: Evaluation (your academic contribution)

Test the research question directly:

- Offline metrics: accuracy, precision/recall/F1 per class, confusion matrix.

- Live vs. dataset check: does the model hold up on real ESP32 readings, which are noisier than dataset values?

- Robustness tests: noisy inputs, boundary values, missing or invalid values, and manual vs. sensor inputs giving consistent results.

- Explainability: which features drive each prediction.

Be honest about limits in the report, such as the small sensor sample and label source. That reads as rigor, not weakness.

## Week 7: Documentation and demo prep

- Architecture diagram, ER diagram, API docs, model comparison table, results, limitations, future work (forecasting, more sensors).

- Write the demo script:

  - Show live sensor data on the dashboard.

  - Put the probe in water or dry soil and show the prediction change.

  - Disconnect the hardware and run the same scenario through manual mode.

  - Show the evaluation results and explanations.

- Record a backup demo video in case Wi-Fi or hardware fails on the day.

## Week 8: Buffer

Bug fixes, rehearsal, and polishing. Don't plan new features here.

## Main risks

- No dataset with a real target label: decide this in Week 1-2, since it affects everything downstream.

- Hardware issues (Wi-Fi, sensor drift): keep manual mode fully working from the start.

- Integration surprises: build a mock /predict in Week 2 so the backend and frontend never wait on the model.

- Scope creep: if you fall behind, cut explainability, then alerts, but never the shared pipeline.